## Sheet1
BUG REPORTS
Bug ID | Title | Test Case ID | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Attachments
BUG_001 | Mobile responsiveness issue | TC_002 | The homepage elements do not adjust properly on mobile devices. Some elements overlap, causing usability issues. | 1. Open the website in a mobile browser. 2. Observe the layout and element alignment. | All elements should adjust properly without overlapping or breaking. | Elements are not adjusting properly, causing overlapping issues. | Medium | High | Open
BUG_002 | Case sensitivity issue in password field | TC_007 | Password is not case-sensitive; users can log in with incorrect case passwords. | 1. Open the login page. 2. Enter a valid username and an incorrect case password. 3. Click the login button. | The system should display an error message 'Invalid username or password.' | User is logged in despite incorrect password case. | High | High | Open | N/A
BUG_003 | Missing password reset functionality | TC_008 | The 'Forgot Password' functionality is not implemented. | 1. Open the login page. 2. Click on the 'Forgot Password' link. 3. Enter a registered email and click submit. | A password reset link should be sent to the registered email. | No action is performed; the feature is missing. | High | High | Open | N/A
BUG_004 | Registration form missing error messages | TC_011 - TC_015 | The registration form does not display required error messages for empty fields, invalid email format, or weak passwords. | 1. Open the registration page. 2. Leave required fields empty / Enter an invalid email / Enter a weak password. 3. Click the 'Register' button. | Error messages should be displayed for missing/invalid inputs. | Error messages are missing. | Medium | High | Open | N/A
BUG_005 | Blog post creation not functioning properly | TC_017 - TC_023 | Users are unable to create posts successfully. Clicking 'Create Post' does not work. | 1. Open the 'Start Writing' or any blog category page. 2. Enter a title, summary, and upload a file. 3. Click the 'Create Post' button. | The post should be created successfully. | Post creation fails. | High | High | Open | N/A
BUG_006 | Footer Link not working function properly | TC_025 | user are to unble footer link successfully.Clicking link does not work. | 1.open the Website and scroolling the page 2.Click the link footer | Link should be successfully created | Not action perfromed the link | High | High | Open | N/A
BUG_007
BUG_008
BUG_009
BUG_010